## Time_table
Working Weeks | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23
Calendar Weeks | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
Start of the week | 2019-12-02 | 2019-12-09 | 2019-12-16 | 2019-12-23 | 2019-12-30 | 2020-01-06 | 2020-01-13 | 2020-01-20 | 2020-01-27 | 2020-02-03 | 2020-02-10 | 2020-02-17 | 2020-02-24 | 2020-03-02 | 2020-03-09 | 2020-03-16 | 2020-03-23 | 2020-03-30 | 2020-04-06 | 2020-04-13 | 2020-04-20 | 2020-04-27 | 2020-05-04 | 2020-05-11
End of the week | 2019-12-08 | 2019-12-15 | 2019-12-22 | 2019-12-29 | 2020-01-05 | 2020-01-12 | 2020-01-19 | 2020-01-26 | 2020-02-02 | 2020-02-09 | 2020-02-16 | 2020-02-23 | 2020-03-01 | 2020-03-08 | 2020-03-15 | 2020-03-22 | 2020-03-29 | 2020-04-05 | 2020-04-12 | 2020-04-19 | 2020-04-26 | 2020-05-03 | 2020-05-10 | 2020-05-17
Image proc. work packages | 2019-12-08: Lane detection
Traffic sign detection
Object detection
Lane detection test and optimize
Tf. Sign de. test and optimize
O.d test and optimize
Other functionalities and optimization
Control work packages | 2019-12-08: Lane keeping control strategy and imp.
Stop strategy and control imp.
Avoidance the collosion with the object
Parallel parking
Other functionalities and optimization
BFMC
Global control stag. and arhitecture work packages | 2019-12-08: High Level Software arhitecture
Global State machine for high level control
Path planning
Test, correcting, finalizing
Other featues
Final result & Demo | 2019-12-08: R. can keep a lane, can make a curve
Robot can stop in front a stop sign with line keeping
R. can avoid the collosion and return the lane, R. can detect pedestrian and stop at pedestrian crossing
Robot is cap to run parallel almost all functionality
Test, optimization and other functionalities
Progress Reports | 2019-12-22: 1st report - 22 dec.; 2020-01-19: 2nd report -19-ian; 2020-02-16: 3rd report - 16 feb; 2020-03-15: 4th report 15.mar; 2020-04-19: 5th report 19.apr

## Task_list
List of Problems & Task: | Task Name: | Task difficulty: | Time Necessity for single person | Comment
Image processing | Rapid frame capture with Rpi camera | Simple | 1 week
| Lane detection | Mediu or Hard | 3-4 week
| Traffic sign detection | Mediu | 2-3 week
| Object detection | Mediu or Hard | 3-4 week
Other
Control | Lane keeping | Simple | 1-2 week | Robot keep the lane based on image proc.
| Parallel Parking | Simple | 1-2 week | Parallel parking
| Object avoidance | Mediu | 2-3 week | Robot avoid an object based in image proc.
| Basic control | Simple | 1-2 week | Can make the minimal curve and forward
Global | High level software arhitecture | Mediu | 2 week | Define the high level soft arhitecture and interfaces between the software parts
| State machine for global strategy | Mediu | 2 week
| Localization and global planning using GPS and Map | Simple | 1 week